## Sheet1
Gissningsapplikation för reklambyrå och dess kunder
Aktivitets- och tidsplan
Projektstart | 2019-12-23
Plan. Projektslut | 2020-02-21
1 sprint = | 1 week
Utvecklare | Carl Schlyter
General plan | REACT General understanding | Database | Rest-API | Database connection | Application features |  |  | Design | Test/Refactoring/Improvements | Sprint | Sprint | PlanHours | PlanDeliveryDate | Weekday | ActlHours | ActDeliveryDate | Weekday | Plan vs Act | Comment
General plan documents | [9 empty] | -3 |  | 8 | 2019-12-18 | Tuesday | 8 | 2019-12-18 | Tuesday | 0
| Rekapitulera REACT | [8 empty] | -2 | -1 | 24 | 2020-01-03 | Friday | 11 | 2020-01-21 Pending | Tuesday | 13
|  | Tables | [7 empty] | 1 |  | 16 | 2020-01-08 | Wednesday
|  | Functions/Queries | [7 empty] | 1 |  | 16 | 2020-01-10 | Friday
|  |  | General understanding | [6 empty] | 2 |  | 16 | 2020-01-14 | Tuesday | 4 | 2020-01-09 | Thursday | 12 | Also incl learning to work with git om a mac
|  |  | Rest-API | [6 empty] | 2 |  | 24 | 2020-01-17 | Friday | 18 | 2020-01-14 Pending |  | 6 | Plus a buch of off office hours, problem making connection to db work
|  |  |  | PDO-connection | [5 empty] | 3 |  | 4 | 2020-01-20 | Monday
[5 empty] | Pages/Components | Features | UserStories
[5 empty] | Registreringssida | Formulär |  |  |  | 3 |  | 4 | 2020-01-20 | Monday
[6 empty] | Funktion |  |  |  | 3 |  | 8 | 2020-01-21 | Tuesday
[5 empty] | Inloggningssida | Formulär |  |  |  | 3 |  | 4 | 2020-01-22 | Wednesday
[6 empty] | Funktion |  |  |  | 3 |  | 8 | 2020-01-23 | Thursday
[5 empty] | Startsida/General | Navigation |  |  |  | 4 |  | 8 | 2020-01-27 | Monday
[6 empty] | Lista med gissningsallternativ |  |  |  | 4 |  | 8 | 2020-01-28 | Tuesday | 9 | 2020-01-22 Pending | Wednesday | -1 | Underestimated this task since it implies starting building own pages with react for the first time
[5 empty] | Gissningssida | Lista med gissningsallternativ |  |  |  | 4 |  | 4 | 2020-01-28 | Tuesday
[6 empty] | Formulär för betting |  |  |  | 4 |  | 4 | 2020-01-29 | Wednesday
[6 empty] | Funktion |  |  |  | 4 |  | 8 | 2020-01-30 | Thursday
[6 empty] | Lista med gjorda bets |  |  |  | 4 |  | 4 | 2020-01-30 | Thursday
[5 empty] | Resultatsida | Lista med gjorda gissningar och rättning |  |  |  | 4 |  | 16 | 2020-02-03 | Monday
[5 empty] | Topplistesida | Lista med gissare och deras totala poäng |  |  |  | 5 |  | 6 | 2020-02-04 | Tuesday
[5 empty] | Adminsida | Lista med reg användare |  |  |  | 5 |  | 4 | 2020-02-05 | Wednesday
[6 empty] | Formulär för ändring |  |  |  | 5 |  | 4 | 2020-02-05 | Wednesday
[6 empty] | Funktion |  |  |  | 5 |  | 8 | 2020-02-06 | Thursday
[8 empty] | General css |  | 5 | 6 | 24 | 2020-02-11 | Tuesday
[8 empty] | Other design |  | 6 |  | 24 | 2020-02-14 | Friday
[9 empty] | Test/Refactoring/Improvements | 7 |  | 40 | 2020-02-21 | Friday
[12 empty] | 294 |  |  | 50 |  |  | 30
[11 empty] | Ant dgr | 36.75 |  | Ant dgr | 6.25 |  |  | 3.75
[14 empty] | % of plan | 17.0068
Added necessairy tasks
[5 empty] | Rekapitulera vanilla js | [9 empty] | 19 | 2020-01-17 | Friday
[14 empty] | Sum added tasks | 19
[14 empty] | Tot ant tim | 69
[14 empty] | Ant dgr | 8.625
[14 empty] | % of plan + added | 22.04%